# # Project Lifecycle Management Guide

# Project Lifecycle Management Guide

This guide outlines the IDEEAS Lab’s project lifecycle: Seed → Active → Completed → Archived. Each stage has specific requirements, deliverables, and approval processes.

## Stage 1: Seed Projects

Purpose: Explore early-stage ideas, conduct feasibility studies, and develop project concepts.

### Entry Criteria

- Initial research idea or question identified

- Potential alignment with lab research thrusts

- Available personnel to explore the concept

- Basic resource requirements understood

### Key Activities

- Literature review and background research

- Feasibility assessment

- Initial methodology development

- Team formation and role definition

- Resource requirement estimation

- Risk assessment

### Required Deliverables

- Project Concept Document (2-3 pages)

  - Research question and significance

  - Preliminary literature review

  - Proposed methodology outline

  - Resource requirements

  - Timeline estimate

- Feasibility Assessment

  - Technical feasibility

  - Resource availability

  - Timeline realism

  - Risk evaluation

- Team Formation Plan

  - Proposed team members and roles

  - Mentoring relationships

  - Collaboration agreements

### Success Criteria

- Clear, answerable research question

- Demonstrated feasibility

- Adequate resources identified

- Team commitment secured

- Alignment with lab mission confirmed

### Stage Duration

Typical: 4-8 weeks Maximum: 12 weeks

### Approval Process

Required for Advancement to Active: - [ ] PI review and approval - [ ] Resource allocation confirmation - [ ] Team member commitment - [ ] IRB approval (if required) - [ ] Complete project brief developed

## Stage 2: Active Projects

Purpose: Execute the research plan, collect and analyze data, and produce deliverables.

### Entry Criteria

- Approved project brief

- Confirmed team and resources

- Clear timeline and milestones

- All necessary approvals obtained

### Key Activities

- Regular progress monitoring

- Data collection and analysis

- Team coordination and communication

- Risk management and issue resolution

- Stakeholder communication

- Deliverable production

### Required Deliverables

- Weekly Progress Reports (using lab template)

- Monthly Milestone Reviews

- Quarterly Comprehensive Reviews

- Risk and Issue Logs (updated regularly)

- Research Outputs (papers, presentations, tools, etc.)

### Management Structure

Project Lead (DRI): - Overall project responsibility - Team coordination - Stakeholder communication - Quality assurance

Team Members: - Specific task ownership - Regular progress reporting - Collaborative problem-solving - Peer support and review

Supervisors/Mentors: - Strategic guidance - Resource support - Quality oversight - Career development support

### Review Schedule

Weekly: Team check-ins and progress updates Monthly: Milestone review and planning Quarterly: Comprehensive project review with PI

### Success Criteria

- Milestones achieved on schedule

- Quality standards maintained

- Team functioning effectively

- Stakeholder expectations met

- Learning objectives achieved

### Stage Duration

Typical: 6-18 months Varies by: Project scope, complexity, and type

### Transition Criteria to Completed

- All major deliverables completed

- Research questions answered

- Results documented and validated

- Dissemination plan executed

- Team learning objectives met

## Stage 3: Completed Projects

Purpose: Finalize outputs, document lessons learned, and transition knowledge.

### Entry Criteria

- All active phase deliverables completed

- Research objectives achieved

- Primary outputs produced

- Team agreement on completion

### Key Activities

- Final documentation and archiving

- Lessons learned capture

- Knowledge transfer

- Output dissemination

- Impact assessment

- Team transition planning

### Required Deliverables

- Final Project Report

  - Executive summary

  - Methodology and results

  - Lessons learned

  - Recommendations

  - Future work suggestions

- Complete Documentation Package

  - All code, data, and analysis files

  - Documentation and README files

  - Reproducibility package

  - Data management plan compliance

- Dissemination Record

  - Publications submitted/published

  - Presentations given

  - Tools/software released

  - Media coverage or impact

- Lessons Learned Document

  - What worked well

  - Challenges and solutions

  - Process improvements

  - Recommendations for future projects

### Knowledge Transfer

Internal Transfer: - Handover to continuing team members - Documentation of institutional knowledge - Training for ongoing maintenance - Integration with other lab projects

External Transfer: - Publication and presentation - Open source releases - Collaboration with external partners - Policy or practice recommendations

### Success Criteria

- All deliverables completed to quality standards

- Knowledge successfully transferred

- Lessons learned documented

- Impact achieved or pathway established

- Team members successfully transitioned

### Stage Duration

Typical: 4-8 weeks Activities: Documentation, dissemination, transition

### Approval Process

Required for Advancement to Archived: - [ ] PI review of final deliverables - [ ] Stakeholder acceptance (if applicable) - [ ] Complete documentation package - [ ] Lessons learned integration - [ ] Team member transition plans

## Stage 4: Archived Projects

Purpose: Preserve project knowledge and outputs for future reference and use.

### Entry Criteria

- All completion requirements met

- Final documentation approved

- Knowledge transfer completed

- No ongoing maintenance required

### Key Activities

- Long-term storage and preservation

- Periodic review for continued relevance

- Reference for future projects

- Historical record maintenance

### Archive Contents

- Complete Project Documentation

- All Research Outputs and Data

- Lessons Learned and Best Practices

- Impact and Follow-up Records

- Team Member Contributions and Recognition

### Access and Maintenance

Access: Available to lab members for reference Maintenance: Minimal, preservation-focused Review: Annual review for continued relevance

## Stage Transition Management

### Transition Reviews

Each stage transition requires a formal review:

Seed → Active Review - Feasibility confirmed - Resources secured - Team committed - Plan approved

Active → Completed Review - Objectives achieved - Deliverables completed - Quality standards met - Dissemination planned

Completed → Archived Review - Documentation complete - Knowledge transferred - Impact assessed - Archival ready

### Decision Authority

Stage Transitions: PI approval required Within-Stage Decisions: Project lead authority Resource Changes: PI approval for significant changes Timeline Extensions: PI approval required

### Documentation Requirements

All stage transitions must be documented with: - Transition date and approver - Rationale for transition - Outstanding issues or risks - Recommendations for next stage

## Best Practices

### Project Planning

- Start with clear, answerable research questions

- Involve all team members in planning

- Build in buffer time for unexpected challenges

- Plan for dissemination from the beginning

### Team Management

- Establish clear roles and responsibilities

- Maintain regular communication rhythms

- Address conflicts early and directly

- Celebrate milestones and achievements

### Quality Assurance

- Regular peer review of work

- Documentation standards compliance

- Reproducibility checks

- External validation when possible

### Risk Management

- Identify risks early and monitor regularly

- Develop contingency plans for major risks

- Communicate risks transparently

- Learn from risk events to improve future projects

Remember: The project lifecycle is designed to ensure quality, accountability, and learning. Use it as a framework, but adapt as needed for your specific project requirements. When in doubt, communicate with your supervisor or the PI.